## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As an admin, I want to connect ticket data via Google Sheets so that the AI can access support history | Must Have | None | Balaji | Done
Sprint 1 | Sprint 1 | US-02 | As a data scientist, I want to collect and preprocess historical ticket data so that the AI model can be trained effectively | Must Have | None | Balaji | Done
Sprint 1 | Sprint 2 | US-03 | As an AI engineer, I want to build a RAG model so that ticket responses can be enriched with knowledge base articles | Must Have | US-02 | Balaji | Done
Sprint 2 | Sprint 2 | US-04 | As a support lead, I want LLMs to categorize tickets by meaning so that support agents can focus better | Must Have | US-03 | Balaji | Done
Sprint 2 | Sprint 2 | US-05 | As a product owner, I want to test the model on a pilot dataset so that I can validate accuracy and usefulness before full deployment | Must Have | US-03 | Balaji | Done
Sprint 2 | Sprint 2 | US-06 | As a data scientist, I want to preprocess ticket data so that models get clean input | Must Have | None | Balaji | Done
Sprint 3 | Sprint 3 | US-07 | As a user, I want to interact with an AI chatbot so that I can resolve my queries instantly | Must Have | None | Balaji | Done
Sprint 3 | Sprint 3 | US-08 | Integrate tools like rag model built, tabuli search to the Agent | Should Have | US-07 | Balaji | Done
Sprint 3 | Sprint 3 | US-09 | As an agent, I want real-time article recommendations so I can resolve tickets faster | Must Have | US-03 | Balaji | Done
Sprint 3 | Sprint 3 | Us-10 | As a manager, I want an analytical dashboard of all tickets so that I can track resolution trends | Should Have | US-09 | Balaji | Done
Sprint 4 | Sprint 4 | US-11 | As a manager, I want dashboards and Slack alerts so I can monitor support gaps easily | Should Have | US-04 | Balaji | Done

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (hours)
US-01 | T-01 | Connect ticket data via Google Sheets | Aug 18 th | Aug 19 th | Balaji | Integration | Done | 8
US-02 | T-02 | Collect and preprocess historical ticket data | Aug 19 th | Aug 21 th | Balaji | Data Preprocessing | Done | 12
US-03 | T-03 | Build RAG model for ticket responses | Aug 21 th | Aug 26 th | Balaji | Model Development | Done | 20
US-04 | T-04 | Categorize tickets using LLMs | Sept 1 st | Sept 6 th | Balaji | Model Integration | Done | 16
US-05 | T-05 | Test model on pilot dataset | Sept 6 th | Sept 8 th | Balaji | Testing | Done | 12
US-06 | T-06 | Preprocess ticket data for clean input | Sept 8 th | Sept 9 th | Balaji | Data Cleaning | Done | 10
US-07 | T-07 | Build AI Chatbot to resolve user queries | Sept 11 th | Sept 15 th | Balaji | Development | Done | 18
US-08 | T-08 | Integrate tools like RAG model, Tabuli search to Agent | Sept 15 th | Sept 18th | Balaji | Integration | Done | 14
US-09 | T-09 | Provide real-time article recommendations | Sept 18 th | Sept 20 th | Balaji | Feature Enhancement | Done | 12
US-10 | T-10 | Build Analytical Dashboard | Sept 20 th | Sept 22 nd | Balaji | Dashboard | Done | 16
US-11 | T-11 | Dashboards and Slack alerts for monitoring | Sept 26 th | Oct 3 rd | Balaji | Monitoring | Done | 14

## Standup Meeting Table
Sprint | Day | Impediments | Action Taken
Sprint 0 | Day 1 | Guidelines to begin up the work | Begin the work
Sprint 1 | Aug 26 th | Discussion on the Implementation of the Sprint 1 | Connected to Google Sheets and Collected the Dataset
Sprint 2 | Sept 9 th | Reasoning behind the low Accuracy | Changed the Chat model to GROQ
Sprint 3 | Sept 22 nd | Various Sentiments in the Classification of Tickets | Changed the categories to only Positive, Negative and Neutral
Sprint 4 | Oct 3 rd | Git Hub Documentation | Completion of Project

## Retrospection
SL | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | Aug 13 th | Aug 29 th | Balaji | Connecting to Google Sheets | Collecting the Database | Building RAG Model | Preprocessing steps implemented
2 | Sprint 2 | Sept 1 st | Sept 10 th | Balaji | Categorizing Tickets | Testing Model with Pilot Dataset | Preprocessing the Data Input | Pilot dataset validated
3 | Sprint 3 | Sept 11 th | Sept 26 th | Balaji | Building the AI Agent | Providing Real time Article Recommendation | Building Analytical Dashboard | Integrated RAG and Tabuli search
4 | Sprint 4 | Sept 26 th | Oct 10 th | Balaji | Monitoring alerts setup | Nil | Nil | Nil